# SmartDQC — 6-Day Development Timeline

New standalone repo. Full UI built from scratch. AI features layered on migrated data pipeline. Deployed as a single Docker image. Daily testing on SE’s laptop (RTX 5060, 8GB VRAM).

Current state: 8 of 16 features complete (Data portion). 8 remaining (full AI portion). Available time: 6 days × 6 hours = 36 hours.

# Day 1 — Foundation & Architecture

Goal: New repo initialised, SLM confirmed working within VRAM budget, existing backend migrated, persistence layer built, documentation written.

- Initialise new SmartDQC git repo; migrate backend from data-cleaning-tool-new

- MyVASS multi-file merge built-in — migrated backend supports uploading N MyVASS files: merge → deduplicate by IC (keep latest DOSE_DATE) → remove null rows. Endpoints: /upload/merge-preview, /eda/run-merged, /download/cleaned-merged

- Docker skeleton — frontend, backend, SLM model server, database containers

- Select and test SLM model (<4B params) on RTX 5060

- Implement persistence layer — dataset library, session history, historical data store, cross-dataset linkage, audit trail

- Write architecture.md, decisions.md, known_issues.md, workflows.md

- Daily test (SE laptop): Features #1–8 pass, dataset persists to history, SLM within VRAM budget. ⚠ Decision gate — do not proceed to Day 2 without confirmed SLM.

# Day 2 — AI Core: Insights, Recommendations & NLQ

Goal: LLM wired into the analysis pipeline, producing BM/English 5W1H-structured output. NLQ working end-to-end.

- Features #9 + #10 (merged): AI narrative module — single LLM call post-analysis producing executive summary + per-indicator insights + recommendations, structured on 5W1H framework (Who, What, When, Where, Why, How)

- Explainability wired in — every AI output states why, not just what (Bahasa Malaysia + English)

- Feature #13: Natural Language Querying — BM/English query → pandas → answer + auto-generated chart

- Daily test (SE laptop): Narrative quality, BM + English accuracy, NLQ on 5 sample queries, response time on SE hardware

# Day 3 — Data Correction & Report Generation

Goal: ML correction detection working. One-click PDF and PPTX report export live.

- Feature #12: ML-based Smart Data Correction Suggestions — decimal shifts, transpositions, column swaps; classifies outliers as entry error vs clinical vs equipment; built as extension of existing cleaning pipeline. Row-level editing UI: users can accept, reject, or manually override each suggestion inline; all edits logged to audit trail.

- Feature #15: Automated Report Generation — reuses Day 2 AI narratives (no duplicate LLM calls); renders MOH-style PDF + PPTX with tables, charts, recommendations, methodology appendix; also auto-generates 9-tab Excel quality report (Executive Summary, Cleaning Rules, Records Dropped, WAZ/HAZ/BAZ × Negeri/Daerah pivots — KPM uses BMI category tabs instead of z-score tabs)

- Daily test (SE laptop): Corrections visible in report, PDF/PPTX opens cleanly on SE machine, no duplicate LLM calls

# Day 4 — Predictive Analytics & Benchmarking

Goal: Risk scoring live per child and per district. Benchmarking dashboard tracking KPIs.

- Feature #11: Predictive Risk Scoring — child-level malnutrition risk using historical Z-scores + demographics; district-level early warning for next-quarter threshold breaches; outputs risk score column + Senarai Kanak-kanak Berisiko

- Feature #16: Benchmarking & Target Tracking — district/state vs national KPIs + WHO targets; traffic-light dashboard (On Track / At Risk / Off Track); AI trajectory narrative per area

- Daily test (SE laptop): Threshold logic, alert generation, AI narrative accuracy; full pipeline: upload → clean → predict → benchmark

# Day 5 — Entity Resolution, Multi-Dataset Analysis & Schema AI

Goal: MVP entity resolution working. User-facing multi-dataset analysis workflow live. Column mapping handling all 3 schema scenarios with AI. Full integration passes.

- Feature #14 (MVP): Cross-Dataset Entity Resolution — IC + DOB match across MyVASS + NCDC + KKM; contradiction detection; unified longitudinal profile per child. Full probabilistic matching is post-v1.

- Multi-Dataset Analysis Workflow — dataset library UI: user browses all past uploads, selects 2+ datasets, triggers a combined/comparative analysis; pipeline handles multiple simultaneous inputs; results show side-by-side comparison, trend deltas, and cross-dataset quality differences

- Feature #2 upgrade: AI-powered schema validation — replace thefuzz with true AI handling all 3 scenarios (exact match / unknown schema / schema drift)

- Daily test (SE laptop): Upload 2 datasets in separate sessions, open dataset library, select both, run combined analysis, verify comparative output. Full end-to-end across all 16 features. If integration passes early, begin UI work.

# Day 6 — Docker, UI (From Scratch) & Final Testing

Goal: Shippable Docker image. Fresh KKM-branded UI live. Full clean end-to-end pass on SE laptop.

- Full Docker containerisation — frontend, backend, SLM, database in one image; no source code exposed; remote maintenance hook for versioned updates

- UI built from scratch — KKM branding + colour scheme, light/dark mode, chatbot interface wired to NLQ

- Final test (SE laptop): Pull Docker image, SE runs full KKM staff workflow end-to-end. Bug fixes only. Tag v1.0.

# Key Risks

- SLM VRAM (Day 1 gate): Must confirm model fits 8GB before Day 2. Swap model if needed.

- Entity Resolution (Day 5): Highest-complexity feature. Scoped to MVP (IC + DOB only). Full probabilistic matching is post-v1.

- UI from scratch (Day 6): Tight timeline. Begin UI work on Day 5 afternoon if integration testing finishes early.

- Data source coverage: v1 targets 4 of 10 sources. Remaining 6 (NHMS, JKN, Parliament, DDSM, Admin Data (1), Admin Data (2)) are post-v1. Note: KPM is v1-supported via clean_kpm() — BMI-based classification (Kurus/Normal/Berlebihan Berat Badan/Obes), not WHO z-scores.

# Open Items

- SLM model selection (blocks Day 1)

- Client predefined business rules — full list not yet received (blocks Feature #5 completeness)

- KKM design assets and branding files (blocks Day 6 UI)

- Feature count confirmation — 16 in document vs 18 stated verbally