## Key Decisions
SmartDQC — Key Decisions & Legend
Colour | Category | Features / Tasks Covered
| Foundation / Infrastructure | Repo, Docker, persistence layer, SLM setup
| AI Features | Insights (#9+#10), NLQ (#13), Risk Scoring (#11), Benchmarking (#16)
| Data Features | Corrections (#12), Reports (#15), Entity Resolution (#14), Schema AI (#2), Multi-Dataset Workflow
| Docker / Deployment | Containerisation, remote maintenance, final packaging
| UI | KKM-branded frontend from scratch, light/dark mode, chatbot
| Testing | Daily SE laptop test — RTX 5060, 8GB VRAM (mandatory — production environment)
Key Decisions Made (2026-05-09 Planning Session)
• Features #9 + #10 merged — one LLM call, one unified output. No separate pipelines.
• Features #9 + #15 share narrative logic — build once, render twice (in-app UI vs PDF/PPTX).
• Feature #12 is the ML layer on top of existing Feature #3 (rule-based) cleaning pipeline.
• Explainability is a cross-cutting requirement (not a feature) — every AI module must explain WHY.
• Schema Mapping AI (Feature #2) is always-on: handles exact match, unknown schema, and schema drift.
• Session History and Multi-Dataset Management are architecture concerns, not standalone features.
• UI is built from scratch — not adapted from data-cleaning-tool frontend. KKM branding, light/dark mode.
• New standalone SmartDQC git repo — clean slate, no dependency on data-cleaning-tool.
• Daily end-of-day testing runs on SE's laptop (RTX 5060, 8GB VRAM) — the production environment.
• Day 1 is a hard decision gate: SLM must pass VRAM test before Day 2 starts.

## Gantt
SmartDQC — 6-Day Development Timeline
Task / Feature | DAY 1 (11/5) Foundation & Architecture |  | DAY 2 (12/5) AI Core + NLQ |  | DAY 3 (13/5) Corrections + Reports |  | DAY 4 (14/5) Predictive + Benchmarking |  | DAY 5 (15/5) Entity / Multi-Dataset / Schema AI |  | DAY 6 (18\5) Docker + UI + Final Test |  | Notes
| Morning (AM) | Afternoon (PM) | Morning (AM) | Afternoon (PM) | Morning (AM) | Afternoon (PM) | Morning (AM) | Afternoon (PM) | Morning (AM) | Afternoon (PM) | Morning (AM) | Afternoon (PM)
FOUNDATION & INFRASTRUCTURE
Backend Migration (#1 - #8)
Docker Skeleton + SLM Selection
Persistence Layer | [12 empty] | Decision gate: SLM must pass VRAM test before Day 2
SLM VRAM Verification
AI CORE
AI Insights + Recommendations (#9+#10)
Natural Language Querying (#13)
DATA CORRECTION + REPORTS
ML Correction Suggestions (#12)
Automated Report Generation (#15)
PREDICTIVE ANALYTICS + BENCHMARKING
Predictive Risk Scoring (#11)
Benchmarking & KPI Dashboard (#16)
ENTITY RESOLUTION + MULTI-DATASET
Entity Resolution (#14)
Multi-Dataset Analysis Workflow
Schema AI Upgrade (#2)
PACKAGING + DEPLOYMENT
Docker Containerisation
UI + Chatbot
DAILY TESTING
Test